## Notes
Tuflow modelling log template
Useful to include job number in file name. (May need to copy log into another job folder at a later date)
Highlight key runs - for example final calibration, results presented to clients or best design event results
Explain any acronyms and abbreviations used on a front Notes page
Use Modelling Log sheet to record progression of model and ECF, TGC, TBC and bc_dbase sheets for more detail where appropriate

## TCF Modelling Log
Project Name: |  | DSITIA flash flooding
Job No: |  | bew457
Modellers: |  | Ellis Symons
Developed from earlier models?
Tuflow build: |  | 2013-12-AC-DP_w64
Location of model files:
Location of results:
Run ID | Date | Modeller | Event/Duration | tcf/ecf | tgc | tbc | Bc_dbase | Changes | Results/Comments
001 | 2014-08-19 | ES |  | WWD_10m_001.tcf |  |  |  | create empty files
002 | 2014-08-19 | ES |  | WWD_10m_002.tcf | WWD_10m_002.tgc |  |  | check domain
003 | 2014-08-19 | ES | Q100_1hr to 3hr | WWD_10m_~e~_003.tcf | WWD_10m_003.tgc | WWD_10m_003.tbc | bc_dbase_003.csv | initial run
004 | 2014-08-19 | ES | Q100_2hr | WWD_10m_~e~_004.tcf | WWD_10m_003.tgc | WWD_10m_004.tbc | bc_dbase_004.csv |  | High MBE in all events
005 | 2014-08-19 | ES | Q50_2hr | WWD_10m_~e~_005.tcf | WWD_10m_005.tgc | WWD_10m_004.tbc | bc_dbase_004.csv | used interpolate ZUVH ALL try and decrease MBE | worsened MBE
006 | 2014-08-19 | ES | Q50_2hr | WWD_10m_~e~_006.tcf | WWD_10m_003.tgc | WWD_10m_004.tbc | bc_dbase_004.csv | changed timestep try and decrease MBE (based on run 004) | worsened MBE
007 | 2014-08-19 | ES | Q50_2hr | WWD_10m_~e~_007.tcf | WWD_10m_003.tgc | WWD_10m_007.tbc | bc_dbase_004.csv | refined ds bndry decrease MBE (moved to a better location) | helped a little
008 | 2014-08-19 | ES | Q50_2hr | WWD_10m_~e~_008.tcf | WWD_10m_008.tgc | WWD_10m_008.tbc | bc_dbase_004.csv | refined dns boundary further to decrease MBE (altered location again) | fixed MBE
009 | 2014-08-19 | ES | ALL | WWD_10m_~e~_009.tcf | WWD_10m_009.tgc | WWD_10m_008.tbc | bc_dbase_004.csv | added a few extra culverts. Enforced rail
010 | 2014-08-20 | ES | ALL | WWD_10m_~e~_010.tcf | WWD_10m_010.tgc | WWD_10m_008.tbc | bc_dbase_004.csv | enforced capricorn highway
011 | 2014-09-09 | ES | ALL | WWD_10m_~e~_011.tcf | WWD_10m_011.tgc | WWD_10m_011.tbc | bc_dbase_011.csv | implemented review suggestions. Incuded roughness changes only )also changed map output to smaller increment)
012 | 2014-09-18 | ES | ALL | WWD_10m_~e~_012.tcf | WWD_10m_012.tgc | WWD_10m_012.tbc | bc_dbase_012.csv | Inflow location for westwood creek was wrong. Changed inflow location

## ECF
1D Control
Date | ECF | New files | Comments

## TGC
Geometry Control
Date | TGC | New files | Comments
2014-08-19 | WWD_10m_002.tgc |  | check domain
2014-08-19 | WWD_10m_003.tgc | 2d_code_003.shp
Westwood_1m_clipped.flt
2d_zsh_culvert_003.shp
2d_mat_LUMP_003.shp
2d_mat_creek_003.shp
2d_zsh_culvert_003_R.shp
2d_zsh_culvert_003_P.shp
2014-08-19 | WWD_10m_005.tgc |  | added interpolate ZUVH ALL command
2014-08-19 | WWD_10m_009.tgc | 2d_zsh_culvert_009_R.shp
2d_zsh_culvert_009_P.shp
2d_zsh_rail_009_L.shp
2d_zsh_rail_009_P.shp
2014-08-20 | WWD_10m_010.tgc | 2d_zsh_road_010_L.shp
2d_zsh_road_010_P.shp
2014-09-09 | WWD_10m_011.tgc |  | no changes. Starting production runs so rev'd up to keep consistent with tcf for control file management purposes
2014-09-18 | WWD_10m_012.tgc | 2d_code_012.shp

## TBC
Boundary Control
Date | TBC | New files | Comments
2014-08-19 | WWD_10m_003.tbc | 2d_sa_003.shp
2d_bc_dns_003.shp
2014-08-19 | WWD_10m_004.tbc | 2d_bc_dns_004.shp
2014-08-19 | WWD_10m_007.tbc | 2d_bc_dns_007.shp
2014-09-09 | WWD_10m_011.tbc |  | no changes. Starting production runs so rev'd up to keep consistent with tcf for control file management purposes
2014-09-18 | WWD_10m_012.tbc | 2d_sa_012.shp | changed inflow location of westwood creek

## bc_dbase
Event Control
Date | bc_dbase | Event Scenario | Comments
2014-08-19 | bc_dbase_003 | Q100_1hr
Q100_2hr
Q100_3hr
2014-08-19 | bc_dbase_004.csv | Q50_2hr
Q100_2hr
Q500_2hr
2014-09-09 | bc_dbase_011.csv | Q50_2hr | no changes to storms. Starting production runs so rev'd up to keep consistent with tcf for control file management purposes
Q100_2hr
Q500_2hr
2014-09-18 | bc_dbase_012.csv | Q50_2hr
Q100_2hr
Q500_2hr

## ds bndry
slope | 0.5% | initial estimate (above)
slope | 0.6% | Final estimate after first run (below

## hydrology
Time of concentration given in peak flow spreadsheet** was 1.2hrs. Westwood has a similar catchment area to Bouldercombe which had a direct rainfall model done and was found to have a 2hr critical duration. Therefore Westwood was assumed to have also have a 2hr critical duration (rounding up the time of concentration estimate).
** | "O:\BRS\Projects\bew\BEW457 - DSITIA Daily Rate Flood Modelling\E - Design Technical\E2 - Input Data\DNRM\Hydrology\Westwood.xlsx"